## Gantt Chart Template
GANTT CHART : Project Face Recognition 2.1 | [27 empty] | https://goo.gl/PlIwL0
| PROJECT TITLE | Build an End to End Image Classification/Recognition Application |  |  |  |  | YEAR | [8 empty] | Master 2 big Data / PFE
| PRODUCTS | Web Application |  |  |  |  | DATE | [8 empty] | May 2022.
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [19 empty] | PHASE THREE | [14 empty] | PHASE FOUR
Data Type | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 14/03/2022 |  |  |  |  | WEEK 2 21/03/2022 |  |  |  |  | WEEK 3 28/03/2022 |  |  |  |  | WEEK 4 04/04/2022 |  |  |  |  | WEEK 5 11/04/2022 |  |  |  |  | WEEK 6 18/04/2022 |  |  |  |  | WEEK 7 25/04/2022 |  |  |  |  | WEEK 8 09/05/2022 |  |  |  |  | WEEK 9 16/05/2022 |  |  |  |  | WEEK 10 23/05/2022 |  |  |  |  | WEEK 11 06/06/2022 |  |  |  |  | WEEK 12 20/06/2022 |  |  |  |  | WEEK 13 27/06/2022
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
BACK END | Deep Learning Algorithms
Sample image data | Training the model on a sample dataset used for face recognition | Ines K | 2022-03-07 | 2022-06-27 | 110 | 100% | bar: WEEK 1 14/03/2022 M to WEEK 2 21/03/2022 F
Sample image data | Choice of parameters for CNN Classifier (testing different models) | Ines K | 2022-03-07 | 2022-06-27 | 110 | 100% | bar: WEEK 1 14/03/2022 M to WEEK 2 21/03/2022 F
Sample image data | Score and Precision comparison for different classifiers (Cost functions ) | Ines K | 2022-03-07 | 2022-06-27 | 110 | 80% | bar: WEEK 2 21/03/2022 M to WEEK 3 28/03/2022 F
BACK END | Deep Learning Algorithms
sample video data | implement webcam test data with openCV | Ines K | 2022-03-07 | 2022-06-27 | 110 | 100% | bar: WEEK 2 21/03/2022 M to WEEK 5 11/04/2022 F
BACK END | Optimization
Sample data | Optimization of face recognition algorithms using multi-fusion feature in the big data environment | Ines K | 2022-03-07 | 2022-06-27 | 110 | 75% | bar: WEEK 4 04/04/2022 F to WEEK 8 09/05/2022 T
Sample data | Integrative interface with powerBI/superset statistics | Ines K | 2022-03-07 | 2022-06-27 | 110 | 50% | bar: WEEK 8 09/05/2022 T to WEEK 12 20/06/2022 F
BACK END | Big Data : Hadoop, Spark/tensorflow
Real Time data | Webcam images dataset (OpenCV) : converting video sequences into images | Ines K | 2022-03-07 | 2022-06-27 | 110 | 100% | bar: WEEK 2 21/03/2022 M to WEEK 5 11/04/2022 F; WEEK 11 06/06/2022 R to WEEK 13 27/06/2022 W
Real Time data | Building an Api used for accessing search results | Ines K | 2022-03-07 | 2022-06-27 | 110 | 20% | bar: WEEK 1 14/03/2022 M to WEEK 2 21/03/2022 F
Real Time data | Parallel video processing on Apache Hadoop clusters | Ines K | 2022-03-07 | 2022-06-27 | 110 | 20% | bar: WEEK 1 14/03/2022 M to WEEK 1 14/03/2022 R
Real Time data | Real-time Image Processing and Analytics using Spark | Ines K | 2022-03-07 | 2022-06-27 | 110 | 10% | bar: WEEK 1 14/03/2022 M to WEEK 1 14/03/2022 W
Real Time data | Real-time Reporting and Stats (Power BI) | Ines K | 2022-03-07 | 2022-06-27 | 110 | 50% | bar: WEEK 10 23/05/2022 F to WEEK 11 06/06/2022 R
FRONT END | Flask Web App
Real Time data | Server : streamline connection to the webcam | Ines K | 2022-03-07 | 2022-06-27 | 110 | 75%
Real Time data | Connecting Big data Algorithms used in phase 2 to real time images from webcam | Ines K | 2022-03-07 | 2022-06-27 | 110 | 20%
Real Time data | HTML web Design of the UI | Ines K | 2022-03-07 | 2022-06-27 | 110 | 30%
PRESENTATION | REPORT
| Writing Project Report |  |  |  |  | 50% | bar: WEEK 1 14/03/2022 M to WEEK 9 16/05/2022 F
| Presentation 1 (Multi-Camera View Face recognition : Google Slides) |  |  |  |  | 100% | WEEK 4 04/04/2022 M: Presented on 06/04/2022.
| Presentation 2 (Face Recognition in Big Data context environment : Canvas) |  |  |  |  | 100% | WEEK 8 09/05/2022 M: Presented on 10/05/2022.
| Final Presentation PFE (July 2022) |  |  |  |  | 10%
OPTIONAL | Android App
Real Time data | Back End : Connecting to the web server ( Api or web app landing page) | Ines K | 2022-03-07 | 2022-06-27 | 110 | 0%
| Front End : Design of the GUI | Ines K | 2022-03-07 | 2022-06-27 | 110 | 0%